PROJECT TIMELINE

Milestone & Delivery Schedule

CCTV AMC & Maintenance Management System

Date: 03 March 2026

# 1. Project Overview

The CCTV AMC & Maintenance Management System will be developed across 7 structured phases over an estimated duration of 7 months (28 Weeks). Phases will overlap where parallel development is possible to optimise the schedule.

# 2. Phase-Wise Timeline

| # | Phase | Duration | Weeks | Key Deliverables |
| --- | --- | --- | --- | --- |
| 1 | Requirements Finalization & UI/UX Design | 3 Weeks | Wk 1–3 | SRS Document, Wireframes, Database Schema, Approval |
| 2 | Backend Architecture & Database Development | 5 Weeks | Wk 3–7 | REST APIs, Database Setup, Auth Module, Role Management |
| 3 | Web Admin Panel Development | 7 Weeks | Wk 4–11 | All admin modules, dashboards, reports, RBAC |
| 4 | Android Mobile Application Development | 7 Weeks | Wk 8–15 | Technician app, offline sync, photo module, PDF reports |
| 5 | Client Login Portal Development | 4 Weeks | Wk 13–16 | Client panel, data isolation, photo viewer, report download |
| 6 | Integration, QA Testing & Bug Fixing | 4 Weeks | Wk 17–20 | End-to-end integration, QA test cases, UAT, performance testing |
| 7 | Deployment, Training & Handover | 2 Weeks | Wk 21–22 | Server deployment, user training, source code & docs handover |
| 8 | Post-Launch Support | 3 Months | Post-Go Live | Bug fixes, minor adjustments, technical support (no new features) |

# 3. Milestone Schedule

| Week | Milestone | Deliverable | Client Sign-Off? |
| --- | --- | --- | --- |
| Wk 3 | SRS & Design Approval | Wireframes, DB Schema, SRS Doc | Yes |
| Wk 7 | Backend Ready | API documentation, DB live | No |
| Wk 11 | Web Admin Panel Ready | Admin panel demo | Yes |
| Wk 15 | Android App Beta Ready | APK for UAT | Yes |
| Wk 16 | Client Portal Ready | Client portal demo | Yes |
| Wk 20 | System Integration Complete | Integrated UAT session | Yes |
| Wk 22 | Go Live & Source Code Handover | Live system + Source code | Yes |

# 4. Assumptions & Conditions

- Timeline begins from the date of project kickoff payment receipt.

- Client must provide timely feedback within 3 business days of each demo.

- Any change in scope or requirements may affect the timeline.

- Timeline assumes availability of server/hosting environment from client side.

- Public holidays and unforeseen events may cause minor adjustments.

# 5. Communication & Review Plan

| Activity | Purpose | Frequency | Mode |
| --- | --- | --- | --- |
| Weekly Status Report | Progress update & issues | Weekly | Email |
| Sprint Review Call | Feature demonstration | Every 2 Weeks | Video Call |
| Milestone Sign-Off | Phase completion approval | Per Milestone | Email / Physical |
| Bug Tracking | Issue reporting & fixing | Daily | Project Portal |